## Task_Report 01-02-2022
REPORT ON TASKS STATUS
1. Tasks scheduled
.No | Group Functions | Screen Name | Content | Description | Status
1 | TEST | Create test spec + test (Cloud) |  | Create test spec and perform testing for Cloud screens: - Login, Register - Camera Management - Camera Configuration - Data Upload - Annotation Output test: Test result with OK/NG | Pending
2 |  | Create test spec + test (Edge) |  | Create test spec and perform testing for Edge screens: - Login, Register - Camera Management + Camera Configuration + Training Video Upload + Configuration Upload - User Administrator - Report Viewer - Statistical Analysis - Target Setting Page/Dialog Output test: Test result with OK/NG | Pending
3 |  | Create test scenario + test |  | Create ~5 case test scenarios for integration b/w Cloud and Edge version: - Cloud: From Register... to output file <CameraName>Configuration.tar.gz - Edge: From Register... to upload configuration (<CameraName>Configuration.tar.gz) train and output reports | Completed
4 | Improvement for Cloud | Camera Management | Update layout Visualize status train of videos | Add socket.io to [Camera Management], show training video (realtime): Camera card color, update status on gateway /report_updating, /report_completion trigger (for now only realtime for camera configuration) Breadcrumbs to be added to the top for navigation purposes : Home > Camera | Completed
5 |  | Camera Configuration | Apply API training video |  | Completed
6 |  |  | Update layout Visualize steps of processing video | Display status of video processing (realtime): Processing compression to 480p, Error while processing compression to 480p, Uploading video to S3, Error while uploading video to S3 Refer to sheet "Video Processing" Camera Configuration to be renamed as "Video Management" Video Management to be a separate page instead of dialog box Thumbnails for each uploaded video shown in grid format 'Add video' button and 'Download Configuration' button (global controls) to be displayed at top right of page Action bar for each thumbnail (contains train, annotate, delete buttons) Duration pill for each thumbnail Breadcrumbs to be added to the top for navigation purposes: Home > Camera > Video | Completed
7 |  | Annotation | Improvement frame images loading | Impore performance on loading video frame: Add the processing of cache frame images (no need to re-load the frames if is it already cached) | Completed
8 |  |  | Clean up frame images after use | Delete data from EC2 after user leaves the annotation screen, help clean up EC2 loading budget | Completed
9 |  | Login/Register | Update layout | Add links to easy travel between screens (not exist in current source code) Breadcrumbs to be added to the top for navigation purposes : Home > [selected camera] > [selected video] > [w1] Renaming of 'Start' and 'End' buttons below video player to 'Cycle Start' and 'Cycle End' Shapes (Polygon/Rectangle) need better deletion methods : 1. better tooltip (informing user to right click to delete) 2. buttons to delete when shape is 'selected' | Completed
10 | Extra functions for Cloud | Company Management |  | Add new module to manage company + bucket: + Only allow (NEC admin) to access + Search companies with Filter, including setting AWS + Delete company On creating company info: + Create Group from AWS Cognito on creating new company + Save to DB: bucket, accessKey, secretAccessKey + Create AWS S3 bucket automatically Automatically apply config for the system (No need seting config.json and restart server) | Pending
11 | Development for Edge | User Administration | Code UI+Logic | - User / Admin login, authentication against local (non AWS) - Role separation - Admins are able to : register users + set targets for workbenches + view the statistical page | Completed
12 |  | Report Viewer | Code UI+Logic | - Reads the reports that fall within the selected date range - Date Range - Scrollable x-axis | Completed
13 |  | Statistical Analysis | Code UI+Logic | - Clean up existing box-and-whisker plot (current one uses Toast UI) - Admins may create and edit groups (of workbenches) on a dialog box in this page | Completed
14 |  | Target Setting Page/Dialog | Code UI+Logic | - Admin only - Admins may select a camera, and then a workbench to specify a upper, lower and target cycle time (in seconds) | Completed
15 |  | Camera Management: AI run | Code logic for train button | Call API (/process) to proceed to TRIGGER and output report for videos | Completed
16 |  |  | Deploy | Deploy on edge (fixed address) | Completed
2. Additional tasks
.No | Issue | Description |  |  | Status
1 | Clear up instance after camera deletion | if user deletes camera half way through a training job, the instance is not terminated and left hanging on the server in the background |  |  | Completed
2 | Stop training from UI | Call API gateway /terminate_instance to terminate instance when user press "stop training" button |  |  | Completed
3 | Message modifications are needed in Camera Management | 1. Processing compression to 480p --> Processing compression 2. Uploading video to S3 --> Uploading video |  |  | Completed
4 | Icon order should be "annotate" --> "train" --> "delete" | Users start from annotate, train then delete. To reduce the stress of users, the icon order must be same as the users' flow. |  |  | Completed
5 | New Annotation Format | The key change here is the addition/moving of the "ROI" field under workbenches
6 | Annotation Page - switching workbench tab forces saving | When switching between workbench tabs, the system forces users to 'submit' the annotation before switching to the next tab. The 'submit' button should be used to submit all the workbenches. |  |  | Completed
7 | Pressing Enter during login page does not log in to account | At login page, pressing "Enter" on the keyboard after typing in credentials does not automatically try to log user in |  |  | Completed
8 | Training "Stage" on the card | If this is temporary design, please ignore this issue. Users know the training runs in the service, but do not know how the system trains the model. Thus, these internal state must be hidden from users' view. Maybe users can understand just progress such as 80%. |  |  | Completed
9 | Change polygon annotation coordinated from referencing 480p video to normalized float variable | Current polygon's annotation on the ***_ct.json file is generated in reference to the downscaled 480p video. This format restricts front end from changing the resolution of the playback video freely since any change in scaled resolution would need to be reflected in the back end as well. |  |  | Completed
10 | Add default Admin account via Docker |  |  |  | Completed
11 | Create "Add User" screen for admin | After creating new user, username and password is shown on screen as a message, so that Admin can copy the values and manually send to New user via email. |  |  | Completed
12 | Stop generating report | Call API gateway /terminate_request to terminate request when user press "stop generating" button |  |  | Completed
13 | Add param "start_date" when call /start_pattern_matching AP | I have made a minor change to the API definitions. Namely the /start_pattern_matching API. I realized we needed 1 more variable from the UI which is the start_date so that the report generation would be accurate. The date time is in the format of YYYY-mm-dd H:M:S GMT+xxxx |  |  | Completed
14 | Update flow generating report with new api gateway /get_system_status | Update flow generating report with new api gateway /get_system_status to check if resources are available before call API /start_inference |  |  | Completed
15 | Add "Change Password" screen |  |  |  | Completed
16 | Display recorded date and time | Shows the recorded date and time of the upload below the creation date on the video card |  |  | Completed
17 | Restricted not use space in camera's name and video's name |  |  |  | Completed
18 | Update "Workbench name" input field become selection field in target setting | Workbench names must be listed up as there's no way to know what workbenches are defined on cloud. This can be gotten from [video]_ct.json file. |  |  | Completed
19 | The range of the value is for the target cycle time, upper target cycle time, lower target cycle times | The range of the value is for the target cycle time, upper target cycle time, lower target cycle time must be [1, 86400]. Negative values cannot be allowed. |  |  | Completed